## 项目规划表
Economy Fueler Project Gantt Chart
CI 103 Introduction to Computing and Information Security | [6 empty] | Cycle highlights: | 19 |  |  | Estimated | [5 empty] | Actual |  |  |  |  | Finished |  |  |  |  | Actual (over plan) | [7 empty] | Finished (over plan)
Task Name | Person in charge | Estimated Start Time | Estimated Duration | Actual Start Time | Actual Duration | Priority | Completion Percentage | Cycle
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Comprehensive Scheduling and Planning | 杨力骁 | 1 | 35 | 6 | 30 | M | 30%
Front End Group | 刘骜宇 | 1 | 16 | 6 | 11 | M | 81.82%
UI Design | 常慧茹 | 1 | 9 | 6 | 4 | L | 100% | Cycle 10: a mature and detailed design for the whole websites.
Login interface and back-end interaction | 刘骜宇 | 6 | 5 | 6 | 5 | L | 100% | Cycle 11: user can login with existed account or register a new one
UI Implementation & Jumping | 刘骜宇 | 11 | 6 | 11 | 6 | H | 66.67% | Cycle 17: complete code for the website which make it usable
Data Group | 曾昕玥 | 6 | 20 | 6 | 20 | M | 45%
File Format Conversion | 曾昕玥、杨力骁、常慧茹 | 6 | 4 | 6 | 4 | L | 100% | Cycle 10: the data can be put into database
Database Architechture Building | 曾昕玥、杨力骁、常慧茹 | 6 | 10 | 6 | 10 | H | 90% | Cycle 16: the definition of data ID, values, keys & EP chart
Database Functions Building | 曾昕玥、杨力骁、常慧茹 | 16 | 11 | 0 | 0 | M | 0% | Cycle 27: support data calculation and data transfer
Algorithm Group | 谢佳和 | 13 | 14 | 13 | 14 | M | 14.29%
Design the Python Script to Extract Data | 谢佳和、刘骜宇、杨力骁 | 13 | 3 | 13 | 3 | H | 67% | Cycle 16: excel-formed data can be taken out to Python console
Design the Ptrhon Script for Calculations | 谢佳和、刘骜宇、杨力骁 | 16 | 3 | 0 | 0 | L | 0% | Cycle 19: complete the calculation formula
Write the Comparison Logic in Django | 谢佳和、刘骜宇、杨力骁 | 18 | 9 | 0 | 0 | L | 0% | Cycle 27: algorithm achievement & display result
Data Visualization Group | 谢佳和 | 23 | 4 | 0 | 0 | L | 0% | Cycle 27: data can show in a form of graph or chart
Finance Group | 杨力骁 | 1 | 23 | 6 | 18 | M | 50%
Material Reading and Research | 杨力骁、常慧茹 | 1 | 23 | 6 | 18 | H | 50% | Cycle 24: understand the related knowlwedge in finance
Finance Analysis Modeling | 杨力骁、常慧茹 | 10 | 11 | 11 | 10 | H | 40% | Cycle 21: find the calculation methods and the meaning of the values
Loan Likelihood Analysis Modeling | 杨力骁、常慧茹 | 21 | 3 | 0 | 0 | L | 0% | Cycle 24: find the calculation methods and the meaning of the values
Back End Group | 谢佳和 | 13 | 16 | 13 | 16 | M | 12.5%
Background Layout Building | 谢佳和、刘骜宇 | 13 | 3 | 13 | 3 | H | 67% | Cycle 16: the appearance of the background page display
Platform Information Display | 谢佳和、刘骜宇 | 23 | 3 | 0 | 0 | L | 0% | Cycle 26: user information display
Background Function Realization | 谢佳和 | 26 | 3 | 0 | 0 | L | 0% | Cycle 29: change the data in the database & manage users
Parallel Testing Phase | 全体成员 | 29 | 7 | 0 | 0 | L | 0%
活动 25 |  | 0 | 0 | 0 | 0 |  | 0%
活动 26 |  | 0 | 0 | 0 | 0 |  | 0%